## Overview
Korea Scholarship Program: 30-Day Calendar
Day 1 Fri 30 Oct 2026 to Day 30 Sat 28 Nov 2026 · two sessions a day: morning (8:30 to 11:30, or 9:00 to 12:00 on Anna days) and afternoon 1:00 to 4:30 · 11 students · Epic Campus
Plan of 29 Oct: English Teacher 1 (Anna) teaches English 9:00 to 12:00 on Wed, Thu and Sat (12 days from 4 Nov), with Korean those afternoons. Other days: Korean mornings, English afternoons with Teacher 3. Week 1 (Days 1, 4, 5) is the grammar foundation with Teacher 2. Korean follows the 24 EStudykorea lessons and the 4 Korean workbooks. Budget and spending are on the Budget tab.
Teaching hours by language
Language | Hours | Share
English | 105 | 54.76%
Korean | 86.75 | 45.24%
Hours by teacher
Teacher | Focus | Confirmed | Sessions | Total hours | Avg hours / day
English Teacher 1 | Anna. Wed, Thu & Sat 9:00 to 12:00: grammar & writing, speaking, mid and final tests, final presentations (12 days) | Yes | 24 | 33 | 1.1
English Teacher 2 | Week 1 grammar foundation + all mock interviews. Free Mon morning, Tue all day, Wed & Thu daytime. Not Saturdays, no evenings | Yes | 13 | 24.75 | 0.825
English Teacher 3 | English afternoons 1:00 to 4:30: reading, vocabulary, listening & IT lab | Yes | 39 | 41 | 1.3667
English Teacher 4 (TBC) | Cover teacher if someone cannot come | To be confirmed | 0 | 0 | 0
Korean Teacher 1 | Korean mornings (staff) | Yes | 30 | 41.25 | 1.375
Korean Teacher 2 | Korean afternoons & Korean IT lab (staff) | Yes | 42 | 45.5 | 1.5167
Colour key
English class
Korean class
IT lab
Activity
Test / interview
Break
Admin
How to use
• Calendar: every session, one row each. Filter by date, teacher or subject.
• Grid: the whole program at a glance, one column per day. Good for printing.
• Days: the theme and focus for each day, plus the IT lab task.
• One tab per teacher with only their sessions.
• To change a teacher, edit the Teacher column on Calendar; totals here update. The live version of this plan is the tracker on epicielts.live.

## Budget
Budget: Korea Scholarship Batch 1
All amounts in LKR. Blue numbers are inputs you can change; black cells are formulas. Yellow cells still need a number. Record every payment on the Spending tab.
1. Income
Item | Amount | Note
Students | 11 | From Ishara, 28 Oct 2026: one more student added (was 10)
Course fee per student | 125000 | From Ishara, 26 Oct 2026
Total course fees | 1375000
Campus share per student | 25000 | From Ishara: LKR 25,000 per student goes to the campus
Campus share total | 275000
Left to budget | 1100000 | The percentages below are applied to this amount
2. Where the money goes
Line | % of budget | Planned (LKR) | Your figure (LKR) | Spent so far (LKR) | Left (LKR) | Status
Campus | 10% | 110000 | 100000 | 0 | 100000 | OK | Percentages and amounts as given by Ishara, 26 Oct 2026
Staff | 40% | 440000 | 400000 | 0 | 400000 | OK
System | 12% | 132000 | 120000 | 0 | 120000 | OK
Web | 10% | 110000 | 100000 | 0 | 100000 | OK
Miscellaneous (transport and other) | 10% | 110000 | 100000 | 0 | 100000 | OK
Accommodation and food | 30% | 330000 | 300000 | 18500 | 281500 | OK
Total | 112% | 1232000 | 1120000 | 18500 | 1101500
Check against the money left to budget | Adds up to 112%, not 100%
Money left after your figures (negative = over budget) | -20000 | Your six lines total more than the money left after the campus share. Lower the % or amounts (blue) until this is zero or positive.
3. Staff costs (inside the Staff line)
Teacher | Pay basis | Rate (LKR) | Units | Cost (LKR) | Status | Hours in the plan | Note | Sessions (half days)
English Teacher 1 | Per session | 5400 | 12 | 64800 | Agreed | 33 | Anna. Wed, Thu & Sat 9:00 to 12:00. LKR 1,800 an hour x 3 hours = 5,400 a session. 12 sessions = 64,800 | 12
Transport: English Teacher 1 | Per session | 2600 | 12 | 31200 | Agreed | 0 | Anna transport, LKR 2,600 a day x 12 days = 31,200 | 12
English Teacher 2 | Per session | 6000 | 8 | 48000 | Suggested | 24.75 | Week 1 grammar + all mock interviews. Mix of 3 h and 3.5 h sessions. Suggested LKR 6,000 a session. Change when agreed | 8
English Teacher 3 | Per month | 55000 | 1 | 55000 | Confirmed | 41 | From Ishara: LKR 55,000 per month, confirmed. English afternoons 1:00 to 4:30 (3.5 h) | 14
English Teacher 4 (TBC) | Per session | 5500 | 0 | 0 | Cover only | 0 | Only paid if they cover a session. Enter sessions covered in column I | 0
Korean Teacher 1 | Staff (no extra cost) | 0 | 0 | 0 | Staff | 41.25 | Campus staff | 15
Korean Teacher 2 | Staff (no extra cost) | 0 | 0 | 0 | Staff | 45.5 | Campus staff | 14
Total staff cost |  |  |  | 199000
Left in the Staff line |  |  |  | 201000
Programme length in months (for monthly pay) | 1 | 30 teaching days = 1 month
4. Per student
Item | Amount (LKR)
Food and accommodation per student per day | 909.0909
Food and accommodation per student, whole programme | 27272.7273
Teaching cost per student (planned staff cost) | 18090.9091
Total budget per student (your figures + campus share) | 126818.1818

## Spending
Spending log
One row per payment. Choose the category from the list so the Budget tab adds it up. The first row is an example: replace or delete it.
Date | Category | What it was for | Amount (LKR) | Paid by | Receipt / note | Total spent | 18500
2026-10-30 | Accommodation and food | Example: rice, vegetables and gas for week 1 | 18500 | Campus office | Example row

## Calendar
Day | Date | Weekday | Week | Start | End | Time | Hours | Session | Type | Language | Teacher | Details
1 | 2026-10-30 | Friday | 1 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Welcome & orientation | Admin |  |  | Rules, timetable, rooms, site logins.
1 | 2026-10-30 | Friday | 1 | 9:00 | 10:45 | 9:00 to 10:45 | 1.75 | English placement test, parts 1 to 3 (IT lab) | Test / interview | English |  | Grammar, vocabulary and reading; listening; writing. On epicielts.live (it opens on first login). Supervised by campus staff.
1 | 2026-10-30 | Friday | 1 | 10:45 | 11:00 | 10:45 to 11:00 | 0.25 | Tea break | Break
1 | 2026-10-30 | Friday | 1 | 11:00 | 11:30 | 11:00 to 11:30 | 0.5 | Getting to know you | Activity | English |  | Names, introductions, what the 30 days look like. Campus staff.
1 | 2026-10-30 | Friday | 1 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
1 | 2026-10-30 | Friday | 1 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | Placement part 4: speaking (one by one) | Test / interview | English | English Teacher 2 | 5 minutes each. Students who are waiting start the parts of speech worksheet.
1 | 2026-10-30 | Friday | 1 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
1 | 2026-10-30 | Friday | 1 | 14:15 | 16:30 | 14:15 to 16:30 | 2.25 | Foundation 1: parts of speech | English class | English | English Teacher 2 | The 8 parts of speech: noun, pronoun, verb, adjective, adverb, preposition, conjunction, interjection. What each one does in a sentence. English workbook 1.
1 | 2026-10-30 | Friday | 1 | 18:30 | 19:30 | 18:30 to 19:30 | 1 | Welcome night & icebreakers | Activity |  |  | Run by campus staff.
2 | 2026-10-31 | Saturday | 1 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Hangul 1: alphabet warm-up + How Hangul works | Korean class | Korean | Korean Teacher 1 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
2 | 2026-10-31 | Saturday | 1 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
2 | 2026-10-31 | Saturday | 1 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Hangul 1: alphabet warm-up + How Hangul works | Korean class | Korean | Korean Teacher 1 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
2 | 2026-10-31 | Saturday | 1 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
2 | 2026-10-31 | Saturday | 1 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Hangul 2: Six starting vowels | Korean class | Korean | Korean Teacher 2 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
2 | 2026-10-31 | Saturday | 1 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
2 | 2026-10-31 | Saturday | 1 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Hangul 2: Six starting vowels | Korean class | Korean | Korean Teacher 2
2 | 2026-10-31 | Saturday | 1 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Hangul 1: alphabet warm-up + How Hangul works" and "Hangul 2: Six starting vowels" on the Korean site.
3 | 2026-11-01 | Sunday | 1 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Hangul 3: The y-vowels | Korean class | Korean | Korean Teacher 1 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
3 | 2026-11-01 | Sunday | 1 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
3 | 2026-11-01 | Sunday | 1 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Hangul 3: The y-vowels | Korean class | Korean | Korean Teacher 1 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
3 | 2026-11-01 | Sunday | 1 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
3 | 2026-11-01 | Sunday | 1 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Hangul 4: Nine starting consonants | Korean class | Korean | Korean Teacher 2 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
3 | 2026-11-01 | Sunday | 1 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
3 | 2026-11-01 | Sunday | 1 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Hangul 4: Nine starting consonants | Korean class | Korean | Korean Teacher 2
3 | 2026-11-01 | Sunday | 1 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Hangul 3: The y-vowels" and "Hangul 4: Nine starting consonants" on the Korean site.
4 | 2026-11-02 | Monday | 1 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Foundation 2: sentence patterns (part 1) | English class | English | English Teacher 2 | How English sentences are built: subject + verb (+ object / complement / place). Word order, questions and negatives with be and do. English workbook 1.
4 | 2026-11-02 | Monday | 1 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
4 | 2026-11-02 | Monday | 1 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Foundation 2: sentence patterns (part 2: practice) | English class | English | English Teacher 2 | Build, speak and write sentences with today's patterns.
4 | 2026-11-02 | Monday | 1 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
4 | 2026-11-02 | Monday | 1 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Foundation 3: pronouns & prepositions (part 1) | English class | English | English Teacher 3 | Subject, object and possessive pronouns; this / that; prepositions of time (at, on, in) and place (in, on, under, next to, between). English workbook 1.
4 | 2026-11-02 | Monday | 1 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
4 | 2026-11-02 | Monday | 1 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Foundation 3: pronouns & prepositions (part 2: practice) | English class | English | English Teacher 3 | Practice in pairs and on paper.
4 | 2026-11-02 | Monday | 1 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | General English > Learn, grammar lessons; repeat today's worksheet tasks on screen.
5 | 2026-11-03 | Tuesday | 1 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Foundation 4: tenses (part 1) | English class | English | English Teacher 2 | The tense timeline: present simple and continuous, past simple, future (will / going to), a first look at present perfect. English workbook 1.
5 | 2026-11-03 | Tuesday | 1 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
5 | 2026-11-03 | Tuesday | 1 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Foundation 4: tenses (part 2: practice) | English class | English | English Teacher 2 | Build, speak and write sentences with today's patterns.
5 | 2026-11-03 | Tuesday | 1 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
5 | 2026-11-03 | Tuesday | 1 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Foundation 5: conjunctions & joining sentences (part 1) | English class | English | English Teacher 2 | and, but, or, so, because, when, before, after. Joining short sentences into longer ones. Week 1 review quiz. English workbook 1.
5 | 2026-11-03 | Tuesday | 1 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
5 | 2026-11-03 | Tuesday | 1 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Foundation 5: conjunctions & joining sentences (part 2: practice) | English class | English | English Teacher 2 | Practice, then the week 1 review quiz.
5 | 2026-11-03 | Tuesday | 1 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 2 | General English > Learn, grammar lessons; repeat today's worksheet tasks on screen.
5 | 2026-11-03 | Tuesday | 1 | 18:30 | 19:30 | 18:30 to 19:30 | 1 | Presentation night #1: "This is me" (2 min each) | Activity | English |  | Run by campus staff. Students use the sentences they built in the week 1 foundation lessons.
6 | 2026-11-04 | Wednesday | 1 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
6 | 2026-11-04 | Wednesday | 1 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | Home & my town. there is / there are; prepositions of place. English workbook 2.
6 | 2026-11-04 | Wednesday | 1 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
6 | 2026-11-04 | Wednesday | 1 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | Home & my town. Describe your home
6 | 2026-11-04 | Wednesday | 1 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
6 | 2026-11-04 | Wednesday | 1 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Hangul 5: Air and consonants | Korean class | Korean | Korean Teacher 2 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
6 | 2026-11-04 | Wednesday | 1 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
6 | 2026-11-04 | Wednesday | 1 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Hangul 5: Air and consonants | Korean class | Korean | Korean Teacher 2
6 | 2026-11-04 | Wednesday | 1 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Hangul 5: Air and consonants" on the Korean site.
7 | 2026-11-05 | Thursday | 2 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
7 | 2026-11-05 | Thursday | 2 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | Food & shopping. Countable / uncountable; some / any. English workbook 2.
7 | 2026-11-05 | Thursday | 2 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
7 | 2026-11-05 | Thursday | 2 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | Food & shopping. Ordering in a café or restaurant
7 | 2026-11-05 | Thursday | 2 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
7 | 2026-11-05 | Thursday | 2 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Hangul 6: Tense consonants | Korean class | Korean | Korean Teacher 2 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
7 | 2026-11-05 | Thursday | 2 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
7 | 2026-11-05 | Thursday | 2 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Hangul 6: Tense consonants | Korean class | Korean | Korean Teacher 2
7 | 2026-11-05 | Thursday | 2 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Hangul 6: Tense consonants" on the Korean site.
8 | 2026-11-06 | Friday | 2 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Review: Hangul 1 to 6 + writing practice | Korean class | Korean | Korean Teacher 1 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
8 | 2026-11-06 | Friday | 2 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
8 | 2026-11-06 | Friday | 2 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Review: Hangul 1 to 6 + writing practice | Korean class | Korean | Korean Teacher 1 | Korean workbook 1. Same lesson on the Korean site for the IT lab.
8 | 2026-11-06 | Friday | 2 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
8 | 2026-11-06 | Friday | 2 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | Home & my town. Places in town. English workbook 2.
8 | 2026-11-06 | Friday | 2 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
8 | 2026-11-06 | Friday | 2 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | Home & my town. Following directions on a map
8 | 2026-11-06 | Friday | 2 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
8 | 2026-11-06 | Friday | 2 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "Home & my town", then its practice questions. Korean: practise "Review: Hangul 1 to 6 + writing practice" on the Korean site.
9 | 2026-11-07 | Saturday | 2 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
9 | 2026-11-07 | Saturday | 2 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | Now and last weekend. Present continuous vs present simple. English workbook 2.
9 | 2026-11-07 | Saturday | 2 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
9 | 2026-11-07 | Saturday | 2 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | Now and last weekend. Describing a picture
9 | 2026-11-07 | Saturday | 2 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
9 | 2026-11-07 | Saturday | 2 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Hangul 7: Eleven more vowels | Korean class | Korean | Korean Teacher 2 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
9 | 2026-11-07 | Saturday | 2 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
9 | 2026-11-07 | Saturday | 2 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Hangul 7: Eleven more vowels | Korean class | Korean | Korean Teacher 2
9 | 2026-11-07 | Saturday | 2 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Hangul 7: Eleven more vowels" on the Korean site.
10 | 2026-11-08 | Sunday | 2 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Hangul 8: Build and write blocks | Korean class | Korean | Korean Teacher 1 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
10 | 2026-11-08 | Sunday | 2 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
10 | 2026-11-08 | Sunday | 2 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Hangul 8: Build and write blocks | Korean class | Korean | Korean Teacher 1 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
10 | 2026-11-08 | Sunday | 2 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
10 | 2026-11-08 | Sunday | 2 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | Food & shopping. Clothes, prices and shops. English workbook 2.
10 | 2026-11-08 | Sunday | 2 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
10 | 2026-11-08 | Sunday | 2 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | Food & shopping. Week 2 review: a day in the city
10 | 2026-11-08 | Sunday | 2 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
10 | 2026-11-08 | Sunday | 2 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "Food & shopping", then its practice questions. Korean: practise "Hangul 8: Build and write blocks" on the Korean site.
11 | 2026-11-09 | Monday | 2 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Hangul 9: Final consonants: batchim | Korean class | Korean | Korean Teacher 1 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
11 | 2026-11-09 | Monday | 2 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
11 | 2026-11-09 | Monday | 2 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Hangul 9: Final consonants: batchim | Korean class | Korean | Korean Teacher 1 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
11 | 2026-11-09 | Monday | 2 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
11 | 2026-11-09 | Monday | 2 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | Now and last weekend. Weekend activities. English workbook 2.
11 | 2026-11-09 | Monday | 2 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
11 | 2026-11-09 | Monday | 2 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | Now and last weekend. A weekend story
11 | 2026-11-09 | Monday | 2 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
11 | 2026-11-09 | Monday | 2 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "Now and last weekend", then its practice questions. Korean: practise "Hangul 9: Final consonants: batchim" on the Korean site.
11 | 2026-11-09 | Monday | 2 | 18:30 | 19:30 | 18:30 to 19:30 | 1 | Debate night #1: City life or village life? | Activity | English |  | Run by campus staff.
12 | 2026-11-10 | Tuesday | 2 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Hangul 10: Link sounds between blocks | Korean class | Korean | Korean Teacher 1 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
12 | 2026-11-10 | Tuesday | 2 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
12 | 2026-11-10 | Tuesday | 2 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Hangul 10: Link sounds between blocks | Korean class | Korean | Korean Teacher 1 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
12 | 2026-11-10 | Tuesday | 2 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
12 | 2026-11-10 | Tuesday | 2 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | Yesterday & school. School subjects and education. English workbook 2.
12 | 2026-11-10 | Tuesday | 2 | 13:00 | 16:30 | 13:00 to 16:30 | 3.5 | Mock scholarship interview round 1 (side room) | Test / interview | English | English Teacher 2 | English Teacher 2 takes students one by one to a side room, 7 minutes each plus written feedback. The rest of the class carries on with the afternoon lesson.
12 | 2026-11-10 | Tuesday | 2 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
12 | 2026-11-10 | Tuesday | 2 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | Yesterday & school. Students talk about school
12 | 2026-11-10 | Tuesday | 2 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
12 | 2026-11-10 | Tuesday | 2 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "Yesterday & school", then its practice questions. Korean: practise "Hangul 10: Link sounds between blocks" on the Korean site.
13 | 2026-11-11 | Wednesday | 3 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
13 | 2026-11-11 | Wednesday | 3 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | Yesterday & school. Past simple of be (was / were). English workbook 2.
13 | 2026-11-11 | Wednesday | 3 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
13 | 2026-11-11 | Wednesday | 3 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | Yesterday & school. Where were you yesterday?
13 | 2026-11-11 | Wednesday | 3 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
13 | 2026-11-11 | Wednesday | 3 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Hangul 11: Double finals and sound changes | Korean class | Korean | Korean Teacher 2 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
13 | 2026-11-11 | Wednesday | 3 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
13 | 2026-11-11 | Wednesday | 3 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Hangul 11: Double finals and sound changes | Korean class | Korean | Korean Teacher 2
13 | 2026-11-11 | Wednesday | 3 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Hangul 11: Double finals and sound changes" on the Korean site.
14 | 2026-11-12 | Thursday | 3 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
14 | 2026-11-12 | Thursday | 3 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | Mid-programme English test: language & reading | Test / interview | English | English Teacher 1
14 | 2026-11-12 | Thursday | 3 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
14 | 2026-11-12 | Thursday | 3 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | Mid-programme English test: writing | Test / interview | English | English Teacher 1
14 | 2026-11-12 | Thursday | 3 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
14 | 2026-11-12 | Thursday | 3 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | Mid-programme English test: listening | Test / interview | English | English Teacher 3
14 | 2026-11-12 | Thursday | 3 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
14 | 2026-11-12 | Thursday | 3 | 14:15 | 16:30 | 14:15 to 16:30 | 2.25 | Mid-programme test: speaking (one by one) + IT lab review | Test / interview | English | English Teacher 3 | Students not being tested review their weak areas in the IT lab.
15 | 2026-11-13 | Friday | 3 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Hangul 12: Read words and sentences | Korean class | Korean | Korean Teacher 1 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
15 | 2026-11-13 | Friday | 3 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
15 | 2026-11-13 | Friday | 3 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Hangul 12: Read words and sentences | Korean class | Korean | Korean Teacher 1 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
15 | 2026-11-13 | Friday | 3 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
15 | 2026-11-13 | Friday | 3 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Mid-programme Korean check (Hangul) | Test / interview | Korean | Korean Teacher 2 | Korean workbook 2. Same lesson on the Korean site for the IT lab.
15 | 2026-11-13 | Friday | 3 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
15 | 2026-11-13 | Friday | 3 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Mid-programme Korean check (Hangul) (continued) | Test / interview | Korean | Korean Teacher 2
15 | 2026-11-13 | Friday | 3 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Hangul 12: Read words and sentences" and "Mid-programme Korean check (Hangul)" on the Korean site.
16 | 2026-11-14 | Saturday | 3 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
16 | 2026-11-14 | Saturday | 3 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | Travel & health. Past simple; first, then, after that, finally. English workbook 3.
16 | 2026-11-14 | Saturday | 3 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
16 | 2026-11-14 | Saturday | 3 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | Travel & health. Telling a short travel story
16 | 2026-11-14 | Saturday | 3 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
16 | 2026-11-14 | Saturday | 3 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Beginner 1 lesson 1: Greetings & introductions | Korean class | Korean | Korean Teacher 2 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
16 | 2026-11-14 | Saturday | 3 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
16 | 2026-11-14 | Saturday | 3 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Beginner 1 lesson 1: Greetings & introductions | Korean class | Korean | Korean Teacher 2
16 | 2026-11-14 | Saturday | 3 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Beginner 1 lesson 1: Greetings & introductions" on the Korean site.
17 | 2026-11-15 | Sunday | 3 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Beginner 1 lesson 2: What is this? | Korean class | Korean | Korean Teacher 1 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
17 | 2026-11-15 | Sunday | 3 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
17 | 2026-11-15 | Sunday | 3 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Beginner 1 lesson 2: What is this? | Korean class | Korean | Korean Teacher 1 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
17 | 2026-11-15 | Sunday | 3 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
17 | 2026-11-15 | Sunday | 3 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | Travel & health. Body, health and the doctor. English workbook 3.
17 | 2026-11-15 | Sunday | 3 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
17 | 2026-11-15 | Sunday | 3 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | Travel & health. At the clinic
17 | 2026-11-15 | Sunday | 3 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
17 | 2026-11-15 | Sunday | 3 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "Travel & health", then its practice questions. Korean: practise "Beginner 1 lesson 2: What is this?" on the Korean site.
17 | 2026-11-15 | Sunday | 3 | 18:30 | 19:30 | 18:30 to 19:30 | 1 | Presentation night #2: "My best memory" | Activity | English |  | Run by campus staff.
18 | 2026-11-16 | Monday | 3 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Beginner 1 lesson 3: Where is it? | Korean class | Korean | Korean Teacher 1 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
18 | 2026-11-16 | Monday | 3 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
18 | 2026-11-16 | Monday | 3 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Beginner 1 lesson 3: Where is it? | Korean class | Korean | Korean Teacher 1 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
18 | 2026-11-16 | Monday | 3 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
18 | 2026-11-16 | Monday | 3 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | English: Review & extra practice | English class | English | English Teacher 3 | Week 3 review: travel, health and the past tense. Extra practice pages + weekly quiz.
18 | 2026-11-16 | Monday | 3 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
18 | 2026-11-16 | Monday | 3 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | English: Speaking practice in pairs | English class | English | English Teacher 3
18 | 2026-11-16 | Monday | 3 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | Weekly General English quiz under Practice.
19 | 2026-11-17 | Tuesday | 4 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Beginner 1 lesson 4: My everyday actions | Korean class | Korean | Korean Teacher 1 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
19 | 2026-11-17 | Tuesday | 4 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
19 | 2026-11-17 | Tuesday | 4 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Beginner 1 lesson 4: My everyday actions | Korean class | Korean | Korean Teacher 1 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
19 | 2026-11-17 | Tuesday | 4 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
19 | 2026-11-17 | Tuesday | 4 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | Plans & careers. Jobs and careers. English workbook 3.
19 | 2026-11-17 | Tuesday | 4 | 13:00 | 16:30 | 13:00 to 16:30 | 3.5 | Mock scholarship interview round 2 (side room) | Test / interview | English | English Teacher 2 | English Teacher 2 takes students one by one to a side room, 7 minutes each plus written feedback. The rest of the class carries on with the afternoon lesson.
19 | 2026-11-17 | Tuesday | 4 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
19 | 2026-11-17 | Tuesday | 4 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | Plans & careers. Advice for a new student
19 | 2026-11-17 | Tuesday | 4 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
19 | 2026-11-17 | Tuesday | 4 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "Plans & careers", then its practice questions. Korean: practise "Beginner 1 lesson 4: My everyday actions" on the Korean site.
20 | 2026-11-18 | Wednesday | 4 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
20 | 2026-11-18 | Wednesday | 4 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | Plans & careers. be going to; future time expressions. English workbook 3.
20 | 2026-11-18 | Wednesday | 4 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
20 | 2026-11-18 | Wednesday | 4 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | Plans & careers. Talking about plans
20 | 2026-11-18 | Wednesday | 4 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
20 | 2026-11-18 | Wednesday | 4 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Beginner 1 lesson 5: Places & going out | Korean class | Korean | Korean Teacher 2 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
20 | 2026-11-18 | Wednesday | 4 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
20 | 2026-11-18 | Wednesday | 4 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Beginner 1 lesson 5: Places & going out | Korean class | Korean | Korean Teacher 2
20 | 2026-11-18 | Wednesday | 4 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Beginner 1 lesson 5: Places & going out" on the Korean site.
21 | 2026-11-19 | Thursday | 4 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
21 | 2026-11-19 | Thursday | 4 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | Studying in Korea. Comparatives and superlatives. English workbook 3.
21 | 2026-11-19 | Thursday | 4 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
21 | 2026-11-19 | Thursday | 4 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | Studying in Korea. Comparing countries and universities
21 | 2026-11-19 | Thursday | 4 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
21 | 2026-11-19 | Thursday | 4 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Beginner 1 lesson 6: Numbers & prices | Korean class | Korean | Korean Teacher 2 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
21 | 2026-11-19 | Thursday | 4 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
21 | 2026-11-19 | Thursday | 4 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Beginner 1 lesson 6: Numbers & prices | Korean class | Korean | Korean Teacher 2
21 | 2026-11-19 | Thursday | 4 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Beginner 1 lesson 6: Numbers & prices" on the Korean site.
22 | 2026-11-20 | Friday | 4 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Review: Beginner 1 lessons 1 to 6 | Korean class | Korean | Korean Teacher 1 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
22 | 2026-11-20 | Friday | 4 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
22 | 2026-11-20 | Friday | 4 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Review: Beginner 1 lessons 1 to 6 | Korean class | Korean | Korean Teacher 1 | Korean workbook 3. Same lesson on the Korean site for the IT lab.
22 | 2026-11-20 | Friday | 4 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
22 | 2026-11-20 | Friday | 4 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | Studying in Korea. Rules, culture and daily life. English workbook 3.
22 | 2026-11-20 | Friday | 4 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
22 | 2026-11-20 | Friday | 4 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | Studying in Korea. Phone calls and appointments
22 | 2026-11-20 | Friday | 4 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
22 | 2026-11-20 | Friday | 4 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "Studying in Korea", then its practice questions. Korean: practise "Review: Beginner 1 lessons 1 to 6" on the Korean site.
23 | 2026-11-21 | Saturday | 4 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
23 | 2026-11-21 | Saturday | 4 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | Emails & goals. Formal vs informal emails. English workbook 4.
23 | 2026-11-21 | Saturday | 4 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
23 | 2026-11-21 | Saturday | 4 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | Emails & goals. Polite requests
23 | 2026-11-21 | Saturday | 4 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
23 | 2026-11-21 | Saturday | 4 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Beginner 1 lesson 7: Shopping & quantities | Korean class | Korean | Korean Teacher 2 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
23 | 2026-11-21 | Saturday | 4 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
23 | 2026-11-21 | Saturday | 4 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Beginner 1 lesson 7: Shopping & quantities | Korean class | Korean | Korean Teacher 2
23 | 2026-11-21 | Saturday | 4 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Beginner 1 lesson 7: Shopping & quantities" on the Korean site.
23 | 2026-11-21 | Saturday | 4 | 18:30 | 19:30 | 18:30 to 19:30 | 1 | Debate night #2: Is studying abroad worth it? | Activity | English |  | Run by campus staff.
24 | 2026-11-22 | Sunday | 4 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Beginner 1 lesson 8: Time & routines | Korean class | Korean | Korean Teacher 1 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
24 | 2026-11-22 | Sunday | 4 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
24 | 2026-11-22 | Sunday | 4 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Beginner 1 lesson 8: Time & routines | Korean class | Korean | Korean Teacher 1 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
24 | 2026-11-22 | Sunday | 4 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
24 | 2026-11-22 | Sunday | 4 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | Emails & goals. Personality and skills. English workbook 4.
24 | 2026-11-22 | Sunday | 4 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
24 | 2026-11-22 | Sunday | 4 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | Emails & goals. Students describe their goals
24 | 2026-11-22 | Sunday | 4 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
24 | 2026-11-22 | Sunday | 4 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "Emails & goals", then its practice questions. Korean: practise "Beginner 1 lesson 8: Time & routines" on the Korean site.
25 | 2026-11-23 | Monday | 5 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Beginner 1 lesson 9: What I do & do not do | Korean class | Korean | Korean Teacher 1 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
25 | 2026-11-23 | Monday | 5 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
25 | 2026-11-23 | Monday | 5 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Beginner 1 lesson 9: What I do & do not do | Korean class | Korean | Korean Teacher 1 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
25 | 2026-11-23 | Monday | 5 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
25 | 2026-11-23 | Monday | 5 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | English: Reading & vocabulary | English class | English | English Teacher 3 | The scholarship interview. Phrases for a personal statement. English workbook 4.
25 | 2026-11-23 | Monday | 5 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
25 | 2026-11-23 | Monday | 5 | 14:15 | 15:15 | 14:15 to 15:15 | 1 | English: Listening | English class | English | English Teacher 3 | The scholarship interview. Feedback on personal statements
25 | 2026-11-23 | Monday | 5 | 15:15 | 15:30 | 15:15 to 15:30 | 0.25 | Short break | Break
25 | 2026-11-23 | Monday | 5 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | English: General English > Learn > "The scholarship interview", then its practice questions. Korean: practise "Beginner 1 lesson 9: What I do & do not do" on the Korean site.
26 | 2026-11-24 | Tuesday | 5 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Beginner 1 lesson 10: What I did yesterday | Korean class | Korean | Korean Teacher 1 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
26 | 2026-11-24 | Tuesday | 5 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
26 | 2026-11-24 | Tuesday | 5 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Beginner 1 lesson 10: What I did yesterday | Korean class | Korean | Korean Teacher 1 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
26 | 2026-11-24 | Tuesday | 5 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
26 | 2026-11-24 | Tuesday | 5 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | English: Review & extra practice | English class | English | English Teacher 3 | Interview language review: point, reason, example. Practise answers in pairs.
26 | 2026-11-24 | Tuesday | 5 | 13:00 | 16:30 | 13:00 to 16:30 | 3.5 | Mock scholarship interview round 3 (side room) | Test / interview | English | English Teacher 2 | English Teacher 2 takes students one by one to a side room, 7 minutes each plus written feedback. The rest of the class carries on with the afternoon lesson.
26 | 2026-11-24 | Tuesday | 5 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
26 | 2026-11-24 | Tuesday | 5 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | English: Speaking practice in pairs | English class | English | English Teacher 3
26 | 2026-11-24 | Tuesday | 5 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: English practice | IT lab | English | English Teacher 3 | Weekly General English quiz under Practice.
27 | 2026-11-25 | Wednesday | 5 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
27 | 2026-11-25 | Wednesday | 5 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | English: Grammar & writing | English class | English | English Teacher 1 | The scholarship interview. Answer structure: point, reason, example. English workbook 4.
27 | 2026-11-25 | Wednesday | 5 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
27 | 2026-11-25 | Wednesday | 5 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | English: Speaking | English class | English | English Teacher 1 | The scholarship interview. Have you ever...? (present perfect)
27 | 2026-11-25 | Wednesday | 5 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
27 | 2026-11-25 | Wednesday | 5 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Beginner 1 lesson 11: What I want to do | Korean class | Korean | Korean Teacher 2 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
27 | 2026-11-25 | Wednesday | 5 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
27 | 2026-11-25 | Wednesday | 5 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Beginner 1 lesson 11: What I want to do | Korean class | Korean | Korean Teacher 2
27 | 2026-11-25 | Wednesday | 5 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Beginner 1 lesson 11: What I want to do" on the Korean site.
28 | 2026-11-26 | Thursday | 5 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
28 | 2026-11-26 | Thursday | 5 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | Final English test: language & reading | Test / interview | English | English Teacher 1
28 | 2026-11-26 | Thursday | 5 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
28 | 2026-11-26 | Thursday | 5 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | Final English test: writing | Test / interview | English | English Teacher 1
28 | 2026-11-26 | Thursday | 5 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
28 | 2026-11-26 | Thursday | 5 | 13:00 | 14:00 | 13:00 to 14:00 | 1 | Final English test: listening | Test / interview | English | English Teacher 3
28 | 2026-11-26 | Thursday | 5 | 14:00 | 14:15 | 14:00 to 14:15 | 0.25 | Short break | Break
28 | 2026-11-26 | Thursday | 5 | 14:15 | 16:30 | 14:15 to 16:30 | 2.25 | Final mock interviews (counts as the final speaking test) | Test / interview | English | English Teacher 2 | English Teacher 2 takes students one by one to a side room, 7 minutes each plus written feedback. The rest of the class carries on with the afternoon lesson.
29 | 2026-11-27 | Friday | 5 | 8:30 | 10:00 | 8:30 to 10:00 | 1.5 | Korean: Beginner 1 lesson 12: Put it all together | Korean class | Korean | Korean Teacher 1 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
29 | 2026-11-27 | Friday | 5 | 10:00 | 10:15 | 10:00 to 10:15 | 0.25 | Tea break | Break
29 | 2026-11-27 | Friday | 5 | 10:15 | 11:30 | 10:15 to 11:30 | 1.25 | Korean practice: Beginner 1 lesson 12: Put it all together | Korean class | Korean | Korean Teacher 1 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
29 | 2026-11-27 | Friday | 5 | 11:30 | 13:00 | 11:30 to 13:00 | 1.5 | Lunch | Break
29 | 2026-11-27 | Friday | 5 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Final Korean test | Test / interview | Korean | Korean Teacher 2 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
29 | 2026-11-27 | Friday | 5 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
29 | 2026-11-27 | Friday | 5 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Final Korean test (continued) | Test / interview | Korean | Korean Teacher 2
29 | 2026-11-27 | Friday | 5 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Beginner 1 lesson 12: Put it all together" and "Final Korean test" on the Korean site.
30 | 2026-11-28 | Saturday | 5 | 8:30 | 9:00 | 8:30 to 9:00 | 0.5 | Morning study time (self-study, campus staff) | Activity |  |  | Revise yesterday's workbook pages.
30 | 2026-11-28 | Saturday | 5 | 9:00 | 10:30 | 9:00 to 10:30 | 1.5 | Final English presentations (part 1) | Activity | English | English Teacher 1
30 | 2026-11-28 | Saturday | 5 | 10:30 | 10:45 | 10:30 to 10:45 | 0.25 | Tea break | Break
30 | 2026-11-28 | Saturday | 5 | 10:45 | 12:00 | 10:45 to 12:00 | 1.25 | Final English presentations (part 2) + programme review | Activity | English | English Teacher 1
30 | 2026-11-28 | Saturday | 5 | 12:00 | 13:00 | 12:00 to 13:00 | 1 | Lunch | Break
30 | 2026-11-28 | Saturday | 5 | 13:00 | 14:30 | 13:00 to 14:30 | 1.5 | Korean: Korean self-introduction (graduation speech practice) | Korean class | Korean | Korean Teacher 2 | Korean workbook 4. Same lesson on the Korean site for the IT lab.
30 | 2026-11-28 | Saturday | 5 | 14:30 | 14:45 | 14:30 to 14:45 | 0.25 | Short break | Break
30 | 2026-11-28 | Saturday | 5 | 14:45 | 15:30 | 14:45 to 15:30 | 0.75 | Korean practice: Korean self-introduction (graduation speech practice) | Korean class | Korean | Korean Teacher 2
30 | 2026-11-28 | Saturday | 5 | 15:30 | 16:30 | 15:30 to 16:30 | 1 | IT lab: Korean practice | IT lab | Korean | Korean Teacher 2 | Korean: practise "Korean self-introduction (graduation speech practice)" on the Korean site.
30 | 2026-11-28 | Saturday | 5 | 18:30 | 19:30 | 18:30 to 19:30 | 1 | Graduation ceremony & certificates | Activity |  |  | Run by campus staff with all teachers invited.

## Grid
Program at a glance
Time | Day 1 Fri 30 Oct | Day 2 Sat 31 Oct | Day 3 Sun 01 Nov | Day 4 Mon 02 Nov | Day 5 Tue 03 Nov | Day 6 Wed 04 Nov | Day 7 Thu 05 Nov | Day 8 Fri 06 Nov | Day 9 Sat 07 Nov | Day 10 Sun 08 Nov | Day 11 Mon 09 Nov | Day 12 Tue 10 Nov | Day 13 Wed 11 Nov | Day 14 Thu 12 Nov | Day 15 Fri 13 Nov | Day 16 Sat 14 Nov | Day 17 Sun 15 Nov | Day 18 Mon 16 Nov | Day 19 Tue 17 Nov | Day 20 Wed 18 Nov | Day 21 Thu 19 Nov | Day 22 Fri 20 Nov | Day 23 Sat 21 Nov | Day 24 Sun 22 Nov | Day 25 Mon 23 Nov | Day 26 Tue 24 Nov | Day 27 Wed 25 Nov | Day 28 Thu 26 Nov | Day 29 Fri 27 Nov | Day 30 Sat 28 Nov
8:30 AM | Welcome & orientation 8:30 to 9:00 | Korean: Hangul 1: alphabet warm-up + How Hangul works 8:30 to 10:00 Korean Teacher 1 | Korean: Hangul 3: The y-vowels 8:30 to 10:00 Korean Teacher 1 | Foundation 2: sentence patterns (part 1) 8:30 to 10:00 English Teacher 2 | Foundation 4: tenses (part 1) 8:30 to 10:00 English Teacher 2 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Korean: Review: Hangul 1 to 6 + writing practice 8:30 to 10:00 Korean Teacher 1 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Korean: Hangul 8: Build and write blocks 8:30 to 10:00 Korean Teacher 1 | Korean: Hangul 9: Final consonants: batchim 8:30 to 10:00 Korean Teacher 1 | Korean: Hangul 10: Link sounds between blocks 8:30 to 10:00 Korean Teacher 1 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Korean: Hangul 12: Read words and sentences 8:30 to 10:00 Korean Teacher 1 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Korean: Beginner 1 lesson 2: What is this? 8:30 to 10:00 Korean Teacher 1 | Korean: Beginner 1 lesson 3: Where is it? 8:30 to 10:00 Korean Teacher 1 | Korean: Beginner 1 lesson 4: My everyday actions 8:30 to 10:00 Korean Teacher 1 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Korean: Review: Beginner 1 lessons 1 to 6 8:30 to 10:00 Korean Teacher 1 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Korean: Beginner 1 lesson 8: Time & routines 8:30 to 10:00 Korean Teacher 1 | Korean: Beginner 1 lesson 9: What I do & do not do 8:30 to 10:00 Korean Teacher 1 | Korean: Beginner 1 lesson 10: What I did yesterday 8:30 to 10:00 Korean Teacher 1 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Morning study time (self-study, campus staff) 8:30 to 9:00 | Korean: Beginner 1 lesson 12: Put it all together 8:30 to 10:00 Korean Teacher 1 | Morning study time (self-study, campus staff) 8:30 to 9:00
9:00 AM | English placement test, parts 1 to 3 (IT lab) 9:00 to 10:45 |  |  |  |  | English: Grammar & writing 9:00 to 10:30 English Teacher 1 | English: Grammar & writing 9:00 to 10:30 English Teacher 1 |  | English: Grammar & writing 9:00 to 10:30 English Teacher 1 |  |  |  | English: Grammar & writing 9:00 to 10:30 English Teacher 1 | Mid-programme English test: language & reading 9:00 to 10:30 English Teacher 1 |  | English: Grammar & writing 9:00 to 10:30 English Teacher 1 |  |  |  | English: Grammar & writing 9:00 to 10:30 English Teacher 1 | English: Grammar & writing 9:00 to 10:30 English Teacher 1 |  | English: Grammar & writing 9:00 to 10:30 English Teacher 1 |  |  |  | English: Grammar & writing 9:00 to 10:30 English Teacher 1 | Final English test: language & reading 9:00 to 10:30 English Teacher 1 |  | Final English presentations (part 1) 9:00 to 10:30 English Teacher 1
10:00 AM |  | Tea break | Tea break | Tea break | Tea break |  |  | Tea break |  | Tea break | Tea break | Tea break |  |  | Tea break |  | Tea break | Tea break | Tea break |  |  | Tea break |  | Tea break | Tea break | Tea break |  |  | Tea break
10:15 AM |  | Korean practice: Hangul 1: alphabet warm-up + How Hangul works 10:15 to 11:30 Korean Teacher 1 | Korean practice: Hangul 3: The y-vowels 10:15 to 11:30 Korean Teacher 1 | Foundation 2: sentence patterns (part 2: practice) 10:15 to 11:30 English Teacher 2 | Foundation 4: tenses (part 2: practice) 10:15 to 11:30 English Teacher 2 |  |  | Korean practice: Review: Hangul 1 to 6 + writing practice 10:15 to 11:30 Korean Teacher 1 |  | Korean practice: Hangul 8: Build and write blocks 10:15 to 11:30 Korean Teacher 1 | Korean practice: Hangul 9: Final consonants: batchim 10:15 to 11:30 Korean Teacher 1 | Korean practice: Hangul 10: Link sounds between blocks 10:15 to 11:30 Korean Teacher 1 |  |  | Korean practice: Hangul 12: Read words and sentences 10:15 to 11:30 Korean Teacher 1 |  | Korean practice: Beginner 1 lesson 2: What is this? 10:15 to 11:30 Korean Teacher 1 | Korean practice: Beginner 1 lesson 3: Where is it? 10:15 to 11:30 Korean Teacher 1 | Korean practice: Beginner 1 lesson 4: My everyday actions 10:15 to 11:30 Korean Teacher 1 |  |  | Korean practice: Review: Beginner 1 lessons 1 to 6 10:15 to 11:30 Korean Teacher 1 |  | Korean practice: Beginner 1 lesson 8: Time & routines 10:15 to 11:30 Korean Teacher 1 | Korean practice: Beginner 1 lesson 9: What I do & do not do 10:15 to 11:30 Korean Teacher 1 | Korean practice: Beginner 1 lesson 10: What I did yesterday 10:15 to 11:30 Korean Teacher 1 |  |  | Korean practice: Beginner 1 lesson 12: Put it all together 10:15 to 11:30 Korean Teacher 1
10:30 AM | [5 empty] | Tea break | Tea break |  | Tea break |  |  |  | Tea break | Tea break |  | Tea break |  |  |  | Tea break | Tea break |  | Tea break |  |  |  | Tea break | Tea break |  | Tea break
10:45 AM | Tea break |  |  |  |  | English: Speaking 10:45 to 12:00 English Teacher 1 | English: Speaking 10:45 to 12:00 English Teacher 1 |  | English: Speaking 10:45 to 12:00 English Teacher 1 |  |  |  | English: Speaking 10:45 to 12:00 English Teacher 1 | Mid-programme English test: writing 10:45 to 12:00 English Teacher 1 |  | English: Speaking 10:45 to 12:00 English Teacher 1 |  |  |  | English: Speaking 10:45 to 12:00 English Teacher 1 | English: Speaking 10:45 to 12:00 English Teacher 1 |  | English: Speaking 10:45 to 12:00 English Teacher 1 |  |  |  | English: Speaking 10:45 to 12:00 English Teacher 1 | Final English test: writing 10:45 to 12:00 English Teacher 1 |  | Final English presentations (part 2) + programme review 10:45 to 12:00 English Teacher 1
11:00 AM | Getting to know you 11:00 to 11:30
11:30 AM | Lunch | Lunch | Lunch | Lunch | Lunch |  |  | Lunch |  | Lunch | Lunch | Lunch |  |  | Lunch |  | Lunch | Lunch | Lunch |  |  | Lunch |  | Lunch | Lunch | Lunch |  |  | Lunch
12:00 PM | [5 empty] | Lunch | Lunch |  | Lunch |  |  |  | Lunch | Lunch |  | Lunch |  |  |  | Lunch | Lunch |  | Lunch |  |  |  | Lunch | Lunch |  | Lunch
1:00 PM | Placement part 4: speaking (one by one) 1:00 to 2:00 English Teacher 2 | Korean: Hangul 2: Six starting vowels 1:00 to 2:30 Korean Teacher 2 | Korean: Hangul 4: Nine starting consonants 1:00 to 2:30 Korean Teacher 2 | Foundation 3: pronouns & prepositions (part 1) 1:00 to 2:30 English Teacher 3 | Foundation 5: conjunctions & joining sentences (part 1) 1:00 to 2:30 English Teacher 2 | Korean: Hangul 5: Air and consonants 1:00 to 2:30 Korean Teacher 2 | Korean: Hangul 6: Tense consonants 1:00 to 2:30 Korean Teacher 2 | English: Reading & vocabulary 1:00 to 2:00 English Teacher 3 | Korean: Hangul 7: Eleven more vowels 1:00 to 2:30 Korean Teacher 2 | English: Reading & vocabulary 1:00 to 2:00 English Teacher 3 | English: Reading & vocabulary 1:00 to 2:00 English Teacher 3 | English: Reading & vocabulary + Mock scholarship interview round 1 (side room) (English Teacher 2) 1:00 to 2:00 English Teacher 3 | Korean: Hangul 11: Double finals and sound changes 1:00 to 2:30 Korean Teacher 2 | Mid-programme English test: listening 1:00 to 2:00 English Teacher 3 | Korean: Mid-programme Korean check (Hangul) 1:00 to 2:30 Korean Teacher 2 | Korean: Beginner 1 lesson 1: Greetings & introductions 1:00 to 2:30 Korean Teacher 2 | English: Reading & vocabulary 1:00 to 2:00 English Teacher 3 | English: Review & extra practice 1:00 to 2:30 English Teacher 3 | English: Reading & vocabulary + Mock scholarship interview round 2 (side room) (English Teacher 2) 1:00 to 2:00 English Teacher 3 | Korean: Beginner 1 lesson 5: Places & going out 1:00 to 2:30 Korean Teacher 2 | Korean: Beginner 1 lesson 6: Numbers & prices 1:00 to 2:30 Korean Teacher 2 | English: Reading & vocabulary 1:00 to 2:00 English Teacher 3 | Korean: Beginner 1 lesson 7: Shopping & quantities 1:00 to 2:30 Korean Teacher 2 | English: Reading & vocabulary 1:00 to 2:00 English Teacher 3 | English: Reading & vocabulary 1:00 to 2:00 English Teacher 3 | English: Review & extra practice + Mock scholarship interview round 3 (side room) (English Teacher 2) 1:00 to 2:30 English Teacher 3 | Korean: Beginner 1 lesson 11: What I want to do 1:00 to 2:30 Korean Teacher 2 | Final English test: listening 1:00 to 2:00 English Teacher 3 | Korean: Final Korean test 1:00 to 2:30 Korean Teacher 2 | Korean: Korean self-introduction (graduation speech practice) 1:00 to 2:30 Korean Teacher 2
2:00 PM | Short break | [6 empty] | Short break |  | Short break | Short break | Short break |  | Short break |  |  | Short break |  | Short break |  |  | Short break |  | Short break | Short break |  |  | Short break
2:15 PM | Foundation 1: parts of speech 2:15 to 4:30 English Teacher 2 | [6 empty] | English: Listening 2:15 to 3:15 English Teacher 3 |  | English: Listening 2:15 to 3:15 English Teacher 3 | English: Listening 2:15 to 3:15 English Teacher 3 | English: Listening 2:15 to 3:15 English Teacher 3 |  | Mid-programme test: speaking (one by one) + IT lab review 2:15 to 4:30 English Teacher 3 |  |  | English: Listening 2:15 to 3:15 English Teacher 3 |  | English: Listening 2:15 to 3:15 English Teacher 3 |  |  | English: Listening 2:15 to 3:15 English Teacher 3 |  | English: Listening 2:15 to 3:15 English Teacher 3 | English: Listening 2:15 to 3:15 English Teacher 3 |  |  | Final mock interviews (counts as the final speaking test) 2:15 to 4:30 English Teacher 2
2:30 PM |  | Short break | Short break | Short break | Short break | Short break | Short break |  | Short break |  |  |  | Short break |  | Short break | Short break |  | Short break |  | Short break | Short break |  | Short break |  |  | Short break | Short break |  | Short break | Short break
2:45 PM |  | Korean practice: Hangul 2: Six starting vowels 2:45 to 3:30 Korean Teacher 2 | Korean practice: Hangul 4: Nine starting consonants 2:45 to 3:30 Korean Teacher 2 | Foundation 3: pronouns & prepositions (part 2: practice) 2:45 to 3:30 English Teacher 3 | Foundation 5: conjunctions & joining sentences (part 2: practice) 2:45 to 3:30 English Teacher 2 | Korean practice: Hangul 5: Air and consonants 2:45 to 3:30 Korean Teacher 2 | Korean practice: Hangul 6: Tense consonants 2:45 to 3:30 Korean Teacher 2 |  | Korean practice: Hangul 7: Eleven more vowels 2:45 to 3:30 Korean Teacher 2 |  |  |  | Korean practice: Hangul 11: Double finals and sound changes 2:45 to 3:30 Korean Teacher 2 |  | Mid-programme Korean check (Hangul) (continued) 2:45 to 3:30 Korean Teacher 2 | Korean practice: Beginner 1 lesson 1: Greetings & introductions 2:45 to 3:30 Korean Teacher 2 |  | English: Speaking practice in pairs 2:45 to 3:30 English Teacher 3 |  | Korean practice: Beginner 1 lesson 5: Places & going out 2:45 to 3:30 Korean Teacher 2 | Korean practice: Beginner 1 lesson 6: Numbers & prices 2:45 to 3:30 Korean Teacher 2 |  | Korean practice: Beginner 1 lesson 7: Shopping & quantities 2:45 to 3:30 Korean Teacher 2 |  |  | English: Speaking practice in pairs 2:45 to 3:30 English Teacher 3 | Korean practice: Beginner 1 lesson 11: What I want to do 2:45 to 3:30 Korean Teacher 2 |  | Final Korean test (continued) 2:45 to 3:30 Korean Teacher 2 | Korean practice: Korean self-introduction (graduation speech practice) 2:45 to 3:30 Korean Teacher 2
3:15 PM | [7 empty] | Short break |  | Short break | Short break | Short break |  |  |  |  | Short break |  | Short break |  |  | Short break |  | Short break | Short break
3:30 PM |  | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: English practice 3:30 to 4:30 English Teacher 2 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 |  | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: English practice 3:30 to 4:30 English Teacher 3 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 |  | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2 | IT lab: Korean practice 3:30 to 4:30 Korean Teacher 2
6:30 PM | Welcome night & icebreakers 6:30 to 7:30 |  |  |  | Presentation night #1: "This is me" (2 min each) 6:30 to 7:30 | [5 empty] | Debate night #1: City life or village life? 6:30 to 7:30 | [5 empty] | Presentation night #2: "My best memory" 6:30 to 7:30 | [5 empty] | Debate night #2: Is studying abroad worth it? 6:30 to 7:30 | [6 empty] | Graduation ceremony & certificates 6:30 to 7:30

## Days
Day | Date | Week | Theme | English focus | Korean focus (suggested) | IT lab task
1 | 2026-10-30 | 1 | Welcome + placement test + Placement speaking + Foundation 1 | Morning: Welcome + placement test Afternoon: Placement speaking + Foundation 1 | No Korean today | English: General English > Learn, revise this week's lessons.
2 | 2026-10-31 | 1 | Korean day: Hangul 1: alphabet warm-up + How Hangul works | No English today | Morning: Hangul 1: alphabet warm-up + How Hangul works Afternoon: Hangul 2: Six starting vowels | Korean: practise "Hangul 1: alphabet warm-up + How Hangul works" and "Hangul 2: Six starting vowels" on the Korean site.
3 | 2026-11-01 | 1 | Korean day: Hangul 3: The y-vowels | No English today | Morning: Hangul 3: The y-vowels Afternoon: Hangul 4: Nine starting consonants | Korean: practise "Hangul 3: The y-vowels" and "Hangul 4: Nine starting consonants" on the Korean site.
4 | 2026-11-02 | 1 | Foundation 2: sentence patterns + Foundation 3: pronouns & prepositions | Morning: Foundation 2: sentence patterns Afternoon: Foundation 3: pronouns & prepositions | No Korean today | English: General English > Learn, revise this week's lessons.
5 | 2026-11-03 | 1 | Foundation 4: tenses + Foundation 5: conjunctions & joining sentences | Morning: Foundation 4: tenses Afternoon: Foundation 5: conjunctions & joining sentences | No Korean today | English: General English > Learn, revise this week's lessons.
6 | 2026-11-04 | 1 | Home & my town (grammar, writing & speaking) | Morning: Home & my town (grammar, writing & speaking) | Afternoon: Hangul 5: Air and consonants | Korean: practise "Hangul 5: Air and consonants" on the Korean site.
7 | 2026-11-05 | 2 | Food & shopping (grammar, writing & speaking) | Morning: Food & shopping (grammar, writing & speaking) | Afternoon: Hangul 6: Tense consonants | Korean: practise "Hangul 6: Tense consonants" on the Korean site.
8 | 2026-11-06 | 2 | Home & my town (reading & listening) | Afternoon: Home & my town (reading & listening) | Morning: Review: Hangul 1 to 6 + writing practice | English: General English > Learn > "Home & my town", then its practice questions. Korean: practise "Review: Hangul 1 to 6 + writing practice" on the Korean site.
9 | 2026-11-07 | 2 | Now and last weekend (grammar, writing & speaking) | Morning: Now and last weekend (grammar, writing & speaking) | Afternoon: Hangul 7: Eleven more vowels | Korean: practise "Hangul 7: Eleven more vowels" on the Korean site.
10 | 2026-11-08 | 2 | Food & shopping (reading & listening) | Afternoon: Food & shopping (reading & listening) | Morning: Hangul 8: Build and write blocks | English: General English > Learn > "Food & shopping", then its practice questions. Korean: practise "Hangul 8: Build and write blocks" on the Korean site.
11 | 2026-11-09 | 2 | Now and last weekend (reading & listening) | Afternoon: Now and last weekend (reading & listening) | Morning: Hangul 9: Final consonants: batchim | English: General English > Learn > "Now and last weekend", then its practice questions. Korean: practise "Hangul 9: Final consonants: batchim" on the Korean site.
12 | 2026-11-10 | 2 | Yesterday & school (reading & listening) | Afternoon: Yesterday & school (reading & listening) | Morning: Hangul 10: Link sounds between blocks | English: General English > Learn > "Yesterday & school", then its practice questions. Korean: practise "Hangul 10: Link sounds between blocks" on the Korean site.
13 | 2026-11-11 | 3 | Yesterday & school (grammar, writing & speaking) | Morning: Yesterday & school (grammar, writing & speaking) | Afternoon: Hangul 11: Double finals and sound changes | Korean: practise "Hangul 11: Double finals and sound changes" on the Korean site.
14 | 2026-11-12 | 3 | Mid-programme English test (part A) + Mid-programme English test (part B) | Morning: Mid-programme English test (part A) Afternoon: Mid-programme English test (part B) | No Korean today | English: General English > Learn, revise this week's lessons.
15 | 2026-11-13 | 3 | Korean day: Hangul 12: Read words and sentences | No English today | Morning: Hangul 12: Read words and sentences Afternoon: Mid-programme Korean check (Hangul) | Korean: practise "Hangul 12: Read words and sentences" and "Mid-programme Korean check (Hangul)" on the Korean site.
16 | 2026-11-14 | 3 | Travel & health (grammar, writing & speaking) | Morning: Travel & health (grammar, writing & speaking) | Afternoon: Beginner 1 lesson 1: Greetings & introductions | Korean: practise "Beginner 1 lesson 1: Greetings & introductions" on the Korean site.
17 | 2026-11-15 | 3 | Travel & health (reading & listening) | Afternoon: Travel & health (reading & listening) | Morning: Beginner 1 lesson 2: What is this? | English: General English > Learn > "Travel & health", then its practice questions. Korean: practise "Beginner 1 lesson 2: What is this?" on the Korean site.
18 | 2026-11-16 | 3 | Review: travel & health, past tense | Afternoon: Review: travel & health, past tense | Morning: Beginner 1 lesson 3: Where is it? | English: General English > Learn, revise this week's lessons. Korean: practise "Beginner 1 lesson 3: Where is it?" on the Korean site.
19 | 2026-11-17 | 4 | Plans & careers (reading & listening) | Afternoon: Plans & careers (reading & listening) | Morning: Beginner 1 lesson 4: My everyday actions | English: General English > Learn > "Plans & careers", then its practice questions. Korean: practise "Beginner 1 lesson 4: My everyday actions" on the Korean site.
20 | 2026-11-18 | 4 | Plans & careers (grammar, writing & speaking) | Morning: Plans & careers (grammar, writing & speaking) | Afternoon: Beginner 1 lesson 5: Places & going out | Korean: practise "Beginner 1 lesson 5: Places & going out" on the Korean site.
21 | 2026-11-19 | 4 | Studying in Korea (grammar, writing & speaking) | Morning: Studying in Korea (grammar, writing & speaking) | Afternoon: Beginner 1 lesson 6: Numbers & prices | Korean: practise "Beginner 1 lesson 6: Numbers & prices" on the Korean site.
22 | 2026-11-20 | 4 | Studying in Korea (reading & listening) | Afternoon: Studying in Korea (reading & listening) | Morning: Review: Beginner 1 lessons 1 to 6 | English: General English > Learn > "Studying in Korea", then its practice questions. Korean: practise "Review: Beginner 1 lessons 1 to 6" on the Korean site.
23 | 2026-11-21 | 4 | Emails & goals (grammar, writing & speaking) | Morning: Emails & goals (grammar, writing & speaking) | Afternoon: Beginner 1 lesson 7: Shopping & quantities | Korean: practise "Beginner 1 lesson 7: Shopping & quantities" on the Korean site.
24 | 2026-11-22 | 4 | Emails & goals (reading & listening) | Afternoon: Emails & goals (reading & listening) | Morning: Beginner 1 lesson 8: Time & routines | English: General English > Learn > "Emails & goals", then its practice questions. Korean: practise "Beginner 1 lesson 8: Time & routines" on the Korean site.
25 | 2026-11-23 | 5 | The scholarship interview (reading & listening) | Afternoon: The scholarship interview (reading & listening) | Morning: Beginner 1 lesson 9: What I do & do not do | English: General English > Learn > "The scholarship interview", then its practice questions. Korean: practise "Beginner 1 lesson 9: What I do & do not do" on the Korean site.
26 | 2026-11-24 | 5 | Review: interview language | Afternoon: Review: interview language | Morning: Beginner 1 lesson 10: What I did yesterday | English: General English > Learn, revise this week's lessons. Korean: practise "Beginner 1 lesson 10: What I did yesterday" on the Korean site.
27 | 2026-11-25 | 5 | The scholarship interview (grammar, writing & speaking) | Morning: The scholarship interview (grammar, writing & speaking) | Afternoon: Beginner 1 lesson 11: What I want to do | Korean: practise "Beginner 1 lesson 11: What I want to do" on the Korean site.
28 | 2026-11-26 | 5 | Final English test (part A) + Final test listening + final mock interviews | Morning: Final English test (part A) Afternoon: Final test listening + final mock interviews | No Korean today | English: General English > Learn, revise this week's lessons.
29 | 2026-11-27 | 5 | Korean day: Beginner 1 lesson 12: Put it all together | No English today | Morning: Beginner 1 lesson 12: Put it all together Afternoon: Final Korean test | Korean: practise "Beginner 1 lesson 12: Put it all together" and "Final Korean test" on the Korean site.
30 | 2026-11-28 | 5 | Final English presentations | Morning: Final English presentations | Afternoon: Korean self-introduction (graduation speech practice) | Korean: practise "Korean self-introduction (graduation speech practice)" on the Korean site.

## English Teacher 1
English Teacher 1
Anna. Wed, Thu & Sat 9:00 to 12:00: grammar & writing, speaking, mid and final tests, final presentations (12 days) · Confirmed
Sessions: | 12 |  | Hours: | 36 |  | One row per session. Hours = start to finish, including the tea break.
Day | Date | Session | Start | End | Hours | What happens in this session | Type
6 | 2026-11-04 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
7 | 2026-11-05 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
9 | 2026-11-07 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
13 | 2026-11-11 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
14 | 2026-11-12 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 Mid-programme English test: language & reading 10:45 to 12:00 Mid-programme English test: writing | Test / interview
16 | 2026-11-14 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
20 | 2026-11-18 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
21 | 2026-11-19 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
23 | 2026-11-21 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
27 | 2026-11-25 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 English: Grammar & writing 10:45 to 12:00 English: Speaking | English class
28 | 2026-11-26 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 Final English test: language & reading 10:45 to 12:00 Final English test: writing | Test / interview
30 | 2026-11-28 | Morning | 9:00 | 12:00 | 3 | 9:00 to 10:30 Final English presentations (part 1) 10:45 to 12:00 Final English presentations (part 2) + programme review | Activity

## English Teacher 2
English Teacher 2
Week 1 grammar foundation + all mock interviews. Free Mon morning, Tue all day, Wed & Thu daytime. Not Saturdays, no evenings · Confirmed
Sessions: | 8 |  | Hours: | 25.75 |  | One row per session. Hours = start to finish, including the tea break. Mock interviews run in a side room during Teacher 3's afternoon.
Day | Date | Session | Start | End | Hours | What happens in this session | Type
1 | 2026-10-30 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 Placement part 4: speaking (one by one) 2:15 to 4:30 Foundation 1: parts of speech | English class + Test / interview
4 | 2026-11-02 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Foundation 2: sentence patterns (part 1) 10:15 to 11:30 Foundation 2: sentence patterns (part 2: practice) | English class
5 | 2026-11-03 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Foundation 4: tenses (part 1) 10:15 to 11:30 Foundation 4: tenses (part 2: practice) | English class
5 | 2026-11-03 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Foundation 5: conjunctions & joining sentences (part 1) 2:45 to 3:30 Foundation 5: conjunctions & joining sentences (part 2: practice) 3:30 to 4:30 IT lab: English practice | English class + IT lab
12 | 2026-11-10 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 4:30 Mock scholarship interview round 1 (side room) | Test / interview
19 | 2026-11-17 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 4:30 Mock scholarship interview round 2 (side room) | Test / interview
26 | 2026-11-24 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 4:30 Mock scholarship interview round 3 (side room) | Test / interview
28 | 2026-11-26 | Afternoon | 14:15 | 16:30 | 2.25 | 2:15 to 4:30 Final mock interviews (counts as the final speaking test) | Test / interview

## English Teacher 3
English Teacher 3
English afternoons 1:00 to 4:30: reading, vocabulary, listening & IT lab · Confirmed
Sessions: | 14 |  | Hours: | 46.5 |  | One row per session. Hours = start to finish, including the tea break.
Day | Date | Session | Start | End | Hours | What happens in this session | Type
4 | 2026-11-02 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Foundation 3: pronouns & prepositions (part 1) 2:45 to 3:30 Foundation 3: pronouns & prepositions (part 2: practice) 3:30 to 4:30 IT lab: English practice | English class + IT lab
8 | 2026-11-06 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
10 | 2026-11-08 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
11 | 2026-11-09 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
12 | 2026-11-10 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
14 | 2026-11-12 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 Mid-programme English test: listening 2:15 to 4:30 Mid-programme test: speaking (one by one) + IT lab review | Test / interview
17 | 2026-11-15 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
18 | 2026-11-16 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 English: Review & extra practice 2:45 to 3:30 English: Speaking practice in pairs 3:30 to 4:30 IT lab: English practice | English class + IT lab
19 | 2026-11-17 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
22 | 2026-11-20 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
24 | 2026-11-22 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
25 | 2026-11-23 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:00 English: Reading & vocabulary 2:15 to 3:15 English: Listening 3:30 to 4:30 IT lab: English practice | English class + IT lab
26 | 2026-11-24 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 English: Review & extra practice 2:45 to 3:30 English: Speaking practice in pairs 3:30 to 4:30 IT lab: English practice | English class + IT lab
28 | 2026-11-26 | Afternoon | 13:00 | 14:00 | 1 | 1:00 to 2:00 Final English test: listening | Test / interview

## English Teacher 4 TBC
English Teacher 4 (TBC)
Cover teacher if someone cannot come · To be confirmed
Sessions: | 0 |  | Hours: | 0 |  | One row per session. Hours = start to finish, including the tea break.
Day | Date | Session | Start | End | Hours | What happens in this session | Type

## Korean Teacher 1
Korean Teacher 1
Korean mornings (staff) · Confirmed
Sessions: | 15 |  | Hours: | 45 |  | One row per session. Hours = start to finish, including the tea break.
Day | Date | Session | Start | End | Hours | What happens in this session | Type
2 | 2026-10-31 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Hangul 1: alphabet warm-up + How Hangul works 10:15 to 11:30 Korean practice: Hangul 1: alphabet warm-up + How Hangul works | Korean class
3 | 2026-11-01 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Hangul 3: The y-vowels 10:15 to 11:30 Korean practice: Hangul 3: The y-vowels | Korean class
8 | 2026-11-06 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Review: Hangul 1 to 6 + writing practice 10:15 to 11:30 Korean practice: Review: Hangul 1 to 6 + writing practice | Korean class
10 | 2026-11-08 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Hangul 8: Build and write blocks 10:15 to 11:30 Korean practice: Hangul 8: Build and write blocks | Korean class
11 | 2026-11-09 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Hangul 9: Final consonants: batchim 10:15 to 11:30 Korean practice: Hangul 9: Final consonants: batchim | Korean class
12 | 2026-11-10 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Hangul 10: Link sounds between blocks 10:15 to 11:30 Korean practice: Hangul 10: Link sounds between blocks | Korean class
15 | 2026-11-13 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Hangul 12: Read words and sentences 10:15 to 11:30 Korean practice: Hangul 12: Read words and sentences | Korean class
17 | 2026-11-15 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Beginner 1 lesson 2: What is this? 10:15 to 11:30 Korean practice: Beginner 1 lesson 2: What is this? | Korean class
18 | 2026-11-16 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Beginner 1 lesson 3: Where is it? 10:15 to 11:30 Korean practice: Beginner 1 lesson 3: Where is it? | Korean class
19 | 2026-11-17 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Beginner 1 lesson 4: My everyday actions 10:15 to 11:30 Korean practice: Beginner 1 lesson 4: My everyday actions | Korean class
22 | 2026-11-20 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Review: Beginner 1 lessons 1 to 6 10:15 to 11:30 Korean practice: Review: Beginner 1 lessons 1 to 6 | Korean class
24 | 2026-11-22 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Beginner 1 lesson 8: Time & routines 10:15 to 11:30 Korean practice: Beginner 1 lesson 8: Time & routines | Korean class
25 | 2026-11-23 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Beginner 1 lesson 9: What I do & do not do 10:15 to 11:30 Korean practice: Beginner 1 lesson 9: What I do & do not do | Korean class
26 | 2026-11-24 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Beginner 1 lesson 10: What I did yesterday 10:15 to 11:30 Korean practice: Beginner 1 lesson 10: What I did yesterday | Korean class
29 | 2026-11-27 | Morning | 8:30 | 11:30 | 3 | 8:30 to 10:00 Korean: Beginner 1 lesson 12: Put it all together 10:15 to 11:30 Korean practice: Beginner 1 lesson 12: Put it all together | Korean class

## Korean Teacher 2
Korean Teacher 2
Korean afternoons & Korean IT lab (staff) · Confirmed
Sessions: | 14 |  | Hours: | 49 |  | One row per session. Hours = start to finish, including the tea break.
Day | Date | Session | Start | End | Hours | What happens in this session | Type
2 | 2026-10-31 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Hangul 2: Six starting vowels 2:45 to 3:30 Korean practice: Hangul 2: Six starting vowels 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
3 | 2026-11-01 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Hangul 4: Nine starting consonants 2:45 to 3:30 Korean practice: Hangul 4: Nine starting consonants 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
6 | 2026-11-04 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Hangul 5: Air and consonants 2:45 to 3:30 Korean practice: Hangul 5: Air and consonants 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
7 | 2026-11-05 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Hangul 6: Tense consonants 2:45 to 3:30 Korean practice: Hangul 6: Tense consonants 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
9 | 2026-11-07 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Hangul 7: Eleven more vowels 2:45 to 3:30 Korean practice: Hangul 7: Eleven more vowels 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
13 | 2026-11-11 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Hangul 11: Double finals and sound changes 2:45 to 3:30 Korean practice: Hangul 11: Double finals and sound changes 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
15 | 2026-11-13 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Mid-programme Korean check (Hangul) 2:45 to 3:30 Mid-programme Korean check (Hangul) (continued) 3:30 to 4:30 IT lab: Korean practice | IT lab + Test / interview
16 | 2026-11-14 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Beginner 1 lesson 1: Greetings & introductions 2:45 to 3:30 Korean practice: Beginner 1 lesson 1: Greetings & introductions 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
20 | 2026-11-18 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Beginner 1 lesson 5: Places & going out 2:45 to 3:30 Korean practice: Beginner 1 lesson 5: Places & going out 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
21 | 2026-11-19 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Beginner 1 lesson 6: Numbers & prices 2:45 to 3:30 Korean practice: Beginner 1 lesson 6: Numbers & prices 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
23 | 2026-11-21 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Beginner 1 lesson 7: Shopping & quantities 2:45 to 3:30 Korean practice: Beginner 1 lesson 7: Shopping & quantities 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
27 | 2026-11-25 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Beginner 1 lesson 11: What I want to do 2:45 to 3:30 Korean practice: Beginner 1 lesson 11: What I want to do 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class
29 | 2026-11-27 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Final Korean test 2:45 to 3:30 Final Korean test (continued) 3:30 to 4:30 IT lab: Korean practice | IT lab + Test / interview
30 | 2026-11-28 | Afternoon | 13:00 | 16:30 | 3.5 | 1:00 to 2:30 Korean: Korean self-introduction (graduation speech practice) 2:45 to 3:30 Korean practice: Korean self-introduction (graduation speech practice) 3:30 to 4:30 IT lab: Korean practice | IT lab + Korean class